## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | Set up repo, environment and tooling. Read core literature. Make early architecture and risk-scoring decisions. Finalise H1-H4 and plan project structure.
Known Risks | Environment/GPU setup may take longer than planned.
2026-04-13 | Done | Create repo and init structure | GitHub repo, folder layout | Programming | Product Quality | 2 | 2 | 0 | repo root
2026-04-13 | Done | Set up Python/CUDA environment | PyTorch, Ultralytics, torchvision install | Programming | Product Quality | 3 | 3 | 0 | requirements.txt
2026-04-14 | Done | Read YOLO/Faster R-CNN/RDD2022/CRDDC papers | Core architecture and benchmark papers | Study | Research Relevance | 3 | 3.5 | 0.5 | references.bib
2026-04-15 | Done | Read OSMnx/routing/PCI literature | Routing and risk-scoring background | Study | Research Relevance | 3 | 3 | 0 | references.bib
2026-04-16 | Done | Decide YOLOv8n vs Faster R-CNN as the two architectures | One-stage vs two-stage comparison | Design | Research Methodology | 1.5 | 1.5 | 0 | thesis 3.2
2026-04-16 | Done | Decide on rule-based (not learned) risk scoring | Auditability over accuracy | Design | Research Methodology | 1 | 1 | 0 | thesis 3.2
2026-04-16 | Done | Supervisor kickoff check-in | Review architecture/risk-scoring decisions and H1-H4 wording | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-04-17 | Done | Finalise H1-H4 wording | From proposal feedback | Design | Research Methodology | 2 | 2 | 0
2026-04-17 | Done | Plan src/ structure and config approach | Folder conventions, config pattern | Planning | Project Management - Process | 2 | 2 | 0
|  |  |  | Total Hours |  | 18 | 18.5 | 0.5
Week 2
week plan: | Explore RDD2022. Decide which classes to keep. Build the small validation dataset. Plan the app page structure.
Known Risks | RDD2022 download and class filtering may surface format issues.
2026-04-20 | Done | Download RDD2022, verify folders/counts | 7 country sources | Research | Research Methodology | 3 | 3 | 0 | data
2026-04-20 | Done | Explore class/country distribution in notebook | First look at the raw pool | Research | Research Methodology | 3 | 3 | 0 | visual dataset inspection notebook
2026-04-21 | Done | Decide to keep 4 damage classes, filter 5th | D00/D10/D20/D40 only | Design | Research Methodology | 3 | 3 | 0 | scripts/
2026-04-21 | Done | Write annotation conversion script | Convert raw RDD2022 labels | Programming | Product Quality | 3 | 3 | 0 | scripts/
2026-04-23 | Done | Build small dataset split (277/60/60) | First dataset scale, for pipeline validation | Programming | Research Methodology | 3 | 3 | 0 | data
2026-04-23 | Done | Verify small dataset integrity | File counts, label format | Testing | Product Quality | 2 | 2 | 0 | scripts
2026-04-23 | Done | Research CVAT for later manual annotation | Tool choice for the Sofia dataset | Study | Research Relevance | 1.5 | 1.5 | 0
2026-04-24 | Done | Plan Streamlit app page structure | Dashboard/Upload/Map/Route pages | Planning | Project Management - Process | 1.5 | 1.5 | 0
|  |  |  | Total Hours |  | 20 | 20 | 0
Week 3
week plan: | Train the first models on the small dataset. Start researching the geospatial and app layers needed for a full pipeline.
Known Risks | Faster R-CNN memory footprint on 8GB GPU is untested.
2026-04-27 | Done | Write YOLOv8n training config | Image size, batch, early stop | Programming | Product Quality | 2 | 2 | 0 | first YOLO training
2026-04-27 | Done | Write Faster R-CNN training config | Grad accumulation, mixed precision | Programming | Product Quality | 3 | 3 | 0 | first YOLO training
2026-04-28 | Done | Debug FRCNN memory errors | 8GB GPU constraint | Debugging | Project Management - Risk | 2 | 2.5 | 0.5 | first FasteRNN training
2026-04-28 | Done | Train YOLOv8n on small dataset | First full run | Programming | Research Methodology | 3 | 3 | 0 | first YOLO training
2026-04-30 | Done | Train Faster R-CNN on small dataset | First full run | Programming | Research Methodology | 4 | 4 | 0 | first FasteRNN training
2026-04-30 | Done | Evaluate both small-dataset models | P/R/F1/mAP | Testing | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-05-01 | Done | Research OSMnx and Folium basics | For the routing/map layers | Study | Research Relevance | 2 | 2 | 0
2026-05-01 | Done | Draft pipeline architecture diagram | First version of the overview figure | Design | Research Methodology | 2 | 2 | 0 | thesis figure 1
|  |  |  | Total Hours |  | 20 | 20.5 | 0.5
Week 4
week plan: | Design and implement the risk-scoring model, so the small-dataset model's output can be scored.
Known Risks | None significant.
2026-05-04 | Done | Design per-detection risk formula | Severity x confidence multiplier | Design | Research Methodology | 2 | 2 | 0 | thesis 3.3
2026-05-04 | Done | Define confidence multiplier function | Floor 0.7, threshold 0.25 | Design | Research Methodology | 3 | 3 | 0 | thesis 3.3
2026-05-05 | Done | Design max+damped-rest combination rule | beta = 0.3 | Design | Research Methodology | 2 | 2 | 0 | thesis 3.3
2026-05-05 | Done | Decide to exclude bbox size from severity | Document rationale | Research | Research Methodology | 1.5 | 1.5 | 0 | thesis 3.3
2026-05-06 | Done | Supervisor check-in | Review risk-scoring model design | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-05-07 | Done | Build risk_weights.yaml | Single config source | Programming | Product Quality | 3 | 3 | 0 | config/risk_weights.yaml
2026-05-07 | Done | Implement src/risk/scoring.py and combine.py | Per-detection scoring + shared combinator | Programming | Product Quality | 3 | 3 | 0 | src/risk/
2026-05-08 | Done | Implement observation_risk.py | [0,1] cap, categories | Programming | Product Quality | 2.5 | 2.5 | 0 | src/risk/observation_risk.py
2026-05-08 | Done | Unit test risk-scoring edge cases | Confidence floor, saturation, combination | Testing | Product Quality | 2 | 2 | 0 | src/risk/
|  |  |  | Total Hours |  | 19.5 | 19.5 | 0
Week 5
week plan: | Build minimal geospatial matching and routing, to prove the full detection-to-route chain works.
Known Risks | OSMnx download of the Sofia graph may be slow or incomplete.
2026-05-11 | Done | Set up Sofia OSM graph download | OSMnx, 8km radius | Programming | Product Quality | 2 | 2 | 0 | src/geospatial/network.py
2026-05-11 | Done | Cache OSM graph locally | Test reload speed | Programming | Product Quality | 1.5 | 1.5 | 0 | src/geospatial/
2026-05-12 | Done | Implement GPS-to-edge matching | 50m threshold | Programming | Product Quality | 3 | 3 | 0 | src/geospatial/
2026-05-12 | Done | Implement segment-level risk aggregation | Total risk + density | Programming | Product Quality | 3 | 3 | 0 | src/risk/segment_aggregation.py
2026-05-14 | Done | Implement risk-aware routing cost c(e) | length + alpha x density | Programming | Product Quality | 2.5 | 2.5 | 0 | src/routing/router.py
2026-05-14 | Done | Run shortest vs risk-aware path on sample detections | Script-level test | Testing | Product Quality | 3 | 3 | 0 | src/routing/
2026-05-15 | Done | Confirm the full chain works end to end (script) | Detection to risk to map to route | Testing | Research Methodology | 4 | 4 | 0
2026-05-15 | Done | Calibrate alpha empirically against first sample data | Early, rough calibration | Research | Research Methodology | 2 | 2 | 0 | config/risk_weights.yaml
|  |  |  | Total Hours |  | 21 | 21 | 0
Week 6
week plan: | Build the first Streamlit app and wire everything together: the working pipeline milestone.
Known Risks | Streamlit page state management may need rework.
2026-05-18 | Done | Build Streamlit app skeleton | Shared config loading | Programming | Product Quality | 2 | 2 | 0 | app.py, pages/
2026-05-18 | Done | Build Upload and Detect page | Upload, run model, confirm-to-store | Programming | Product Usefulness | 3 | 3 | 0 | pages/2_Upload_Detect.py
2026-05-19 | Done | Design and build SQLite schema | 4 tables | Design | Product Quality | 3 | 3 | 0 | src/app/database.py
2026-05-19 | Done | Build basic Dashboard page | Summary stats, overview map | Programming | Product Usefulness | 2 | 2 | 0 | pages/1_Dashboard.py
2026-05-18 | Done | Supervisor check-in | Demo the first working model | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-05-21 | Done | Build basic Damage Map page | Markers, segment colouring | Programming | Product Usefulness | 2.5 | 2.5 | 0 | pages/3_Damage_Map.py
2026-05-21 | Done | Build basic Safer Route Planner page | Origin/destination, route comparison | Programming | Product Usefulness | 2.5 | 2.5 | 0 | pages/4_Safer_Route_Planner.py
2026-05-22 | Done | Full first end-to-end walkthrough test | Milestone: pipeline complete | Testing | Product Quality | 2.5 | 2.5 | 0 |  | first working pipeline
2026-05-22 | Done | Fix bugs found in first walkthrough | Upload/map/routing glitches | Debugging | Product Quality | 2 | 2 | 0
|  |  |  | Total Hours |  | 20 | 20 | 0
Week 7
week plan: | Go back to training: audit dataset bias and retrain on a medium-scale dataset.
Known Risks | Bias found in the small dataset may require a bigger-than-planned rebuild.
2026-05-25 | Done | Audit class balance of small-dataset results | Check D00 vs D20/D40 ratios | Research | Research Methodology | 2 | 2 | 0 | notebooks/
2026-05-25 | Done | Audit country balance | Japan share vs raw pool | Research | Research Methodology | 2 | 2 | 0 | notebooks/
2026-05-26 | Done | Confirm D00 2-3x overrepresentation | Vs. D20/D40 | Research | Project Management - Risk | 1.5 | 1.5 | 0 | notebooks/ | bias found
2026-05-26 | Done | Confirm Japan ~46% vs ~28% raw | Country skew | Research | Project Management - Risk | 1.5 | 1.5 | 0 | notebooks/ | bias found
2026-05-28 | Done | Build medium dataset split (1,034/224/221) | Second dataset scale | Programming | Research Methodology | 3 | 3 | 0 | data/processed/medium/
2026-05-28 | Done | Train YOLOv8n on medium dataset | Confirm imbalance effect | Programming | Research Methodology | 3 | 3 | 0 | runs/
2026-05-29 | Done | Train Faster R-CNN on medium dataset | Confirm imbalance effect | Programming | Research Methodology | 3 | 3.5 | 0.5 | runs/
2026-05-29 | Done | Evaluate medium-dataset models | P/R/F1/mAP | Testing | Research Methodology | 2.5 | 2.5 | 0 | outputs/reports/
|  |  |  | Total Hours |  | 18.5 | 19 | 0.5
Week 8
week plan: | Design and build the balanced large dataset.
Known Risks | D40 (pothole) has zero images from 3 of 7 countries; quota maths must account for this.
2026-06-01 | Done | Design water-filling balancing algorithm | Per-class quota across countries | Design | Research Methodology | 3 | 3 | 0 | scripts/
2026-06-01 | Done | Handle D40's 4-country constraint | Zero pothole images from 3 countries | Programming | Research Methodology | 2 | 2 | 0 | scripts/
2026-06-02 | Done | Implement balancing script | Water-filling allocation | Programming | Product Quality | 3 | 3 | 0 | scripts/
2026-06-02 | Done | Unit test balancing script | D40 4-country constraint | Testing | Product Quality | 2 | 2 | 0 | scripts/
2026-06-04 | Done | Run balancing script, build large dataset | 4,291/597/592 | Programming | Research Methodology | 3 | 3 | 0 | data/processed/large/
2026-06-04 | Done | Verify balancing output | Counts match quotas | Testing | Research Methodology | 2 | 2 | 0 | thesis Table A.1
2026-06-05 | Done | Add damage-free negatives | 200/30 images | Programming | Product Quality | 1.5 | 1.5 | 0 | data/processed/large/
|  |  |  | Total Hours |  | 16.5 | 16.5 | 0
Week 9
week plan: | Train both models on the large dataset and evaluate; discover Faster R-CNN's overfitting pattern.
Known Risks | Faster R-CNN may hit the same GPU memory issue at larger scale.
2026-06-08 | Done | Train YOLOv8n on large dataset | Monitor run | Programming | Research Methodology | 3 | 3 | 0 | runs/
2026-06-08 | Done | Train Faster R-CNN on large dataset | Monitor run | Programming | Research Methodology | 3 | 3 | 0 | models/fasterrcnn_large/
2026-06-09 | Done | Debug FRCNN GPU memory error, resume training | Restart from checkpoint | Debugging | Project Management - Risk | 2 | 2.5 | 0.5 | notebooks/
2026-06-09 | Done | Evaluate YOLOv8n (large dataset) | Full metrics | Testing | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-11 | Done | Evaluate Faster R-CNN (large dataset) | Full metrics | Testing | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-11 | Done | Compute per-class mAP50-95 for both models | D40 strongest after balancing | Research | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-12 | Done | Review FRCNN loss curves | Best checkpoint at epoch 2 of 22 | Debugging | Project Management - Risk | 2 | 2 | 0 | notebooks/ | overfitting found
2026-06-12 | Done | Try reduced LR / increased patience on FRCNN | Attempts to curb overfitting | Debugging | Project Management - Risk | 2 | 2 | 0 | notebooks/ | unresolved
|  |  |  | Total Hours |  | 18 | 18.5 | 0.5
Week 10
week plan: | Run the H1 statistical tests and write up the model-comparison result.
Known Risks | None significant.
2026-06-15 | Done | Document FRCNN overfitting as accepted limitation | Decision to report, not chase further | Research | Research Methodology | 2 | 2 | 0 | thesis 5.4
2026-06-15 | Done | Measure per-image inference time | Same 592 images, same session | Testing | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-16 | Done | Run Wilcoxon signed-rank test on inference time | H1 complexity criterion | Research | Research Methodology | 2.5 | 2.5 | 0 | outputs/reports/
2026-06-16 | Done | Run bootstrap CI on mAP50-95 difference | H1 accuracy criterion | Research | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-17 | Done | Supervisor check-in | Review H1 result and the FRCNN overfitting decision | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-06-18 | Done | Measure training wall-clock time (both models) | Identical hardware | Research | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-06-18 | Done | Re-run small/medium/large comparison table | For the thesis iterations table | Research | Research Methodology | 3 | 3 | 0 | thesis Table 2
2026-06-19 | Done | Update pipeline diagram with H1-H4 tags | Final version of figure 1 | Design | Professionalism - Communication | 1.5 | 1.5 | 0 | thesis figure 1
2026-06-19 | Done | Draft H1 Results and Discussion write-up | Section 4.1.3 / 5.1 | Evidencing | Professionalism - Communication | 2.5 | 2.5 | 0 | thesis 4.1.3
|  |  |  | Total Hours |  | 18 | 18 | 0
Week 11
week plan: | Collect and annotate the first manual Sofia dataset (for domain-adaptation fine-tuning).
Known Risks | Driving video collection depends on weather and traffic.
2026-06-29 | Done | Plan manual Sofia data collection | Route, method | Planning | Project Management - Process | 2 | 2 | 0 | thesis 3.6
2026-06-29 | Done | Test recording setup | Phone mounted in car | Programming | Product Quality | 1 | 1 | 0
2026-06-30 | Done | Collect driving video (session 1) | Public roads around Sofia | Research | Research Methodology | 4 | 4 | 0 | data/manual/
2026-07-02 | Done | Collect driving video (session 2) | Continued coverage | Research | Research Methodology | 3 | 3 | 0 | data/manual/
2026-07-02 | Done | Extract candidate damage frames from video | From both sessions | Programming | Research Methodology | 3 | 3 | 0 | data/manual/images/
2026-07-03 | Done | Annotate in CVAT - D00/D10 classes | Bounding boxes | Programming | Product Quality | 3 | 3 | 0 | data/manual/labels/
2026-07-03 | Done | Annotate in CVAT - D20/D40 classes | Bounding boxes | Programming | Product Quality | 3 | 3 | 0 | data/manual/labels/
|  |  |  | Total Hours |  | 19 | 19 | 0
Week 12
week plan: | Finish annotation and fine-tune both models on the manual Sofia data.
Known Risks | Fine-tuning hyperparameters are untested on this small a dataset.
2026-07-06 | Done | Export annotations, verify format, fix mismatches | YOLO Detection 1.0 format | Testing | Product Quality | 3 | 3 | 0 | data/manual/labels/
2026-07-06 | Done | Audit manual-set class distribution | 150/75/90/35 images per class | Research | Research Methodology | 1 | 1 | 0 | thesis 3.6
2026-07-07 | Done | Split fine-tune train/val/test | 131/28/42, non-overlapping | Programming | Research Methodology | 2 | 2 | 0 | thesis Table: Sofia split
2026-07-07 | Done | Baseline-evaluate both models on Sofia test set | No fine-tuning yet | Testing | Research Methodology | 2.5 | 2.5 | 0 | outputs/reports/ | domain gap found
2026-07-08 | Done | Supervisor check-in | Review domain-adaptation results | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-07-09 | Done | Design fine-tuning protocol | Reduced LR, short epoch budget | Design | Research Methodology | 2 | 2 | 0 | notebooks/
2026-07-09 | Done | Fine-tune YOLOv8n on 131-image split | From RDD2022-large weights | Programming | Research Methodology | 3 | 3 | 0 | models/yolov8n_sofia_finetune/
2026-07-10 | Done | Fine-tune Faster R-CNN on 131-image split | Same protocol | Programming | Research Methodology | 3.5 | 3.5 | 0 | models/fasterrcnn_sofia_finetune/
2026-07-10 | Done | Evaluate fine-tuned models, analyse domain-adaptation gains | Before/after comparison | Testing | Research Methodology | 3 | 3 | 0 | thesis 5.2
|  |  |  | Total Hours |  | 20.5 | 20.5 | 0
Week 13
week plan: | Rebuild the app around the fine-tuned model and finish the remaining pages.
Known Risks | None significant.
2026-07-27 | Done | Swap app's active model to fine-tuned YOLOv8n | Update app_config.yaml | Programming | Product Quality | 2 | 2 | 0 | config/app_config.yaml
2026-07-27 | Done | Rebuild Damage Map - segment colouring, heatmap layer | Full version | Programming | Product Usefulness | 3 | 3 | 0 | pages/3_Damage_Map.py
2026-07-28 | Done | Rebuild Safer Route Planner - alpha slider, comparison display | Full version | Programming | Product Usefulness | 3 | 3 | 0 | pages/4_Safer_Route_Planner.py
2026-07-28 | Done | Record distance-increase per route | Logged, not enforced | Programming | Product Quality | 2 | 2 | 0 | src/app/database.py
2026-07-30 | Done | Full app walkthrough test with fine-tuned model | Upload to route planner | Testing | Product Quality | 2.5 | 2.5 | 0
2026-07-30 | Done | Fix marker/map-centring/duplicate-upload bugs | From walkthrough | Debugging | Product Quality | 2.5 | 2.5 | 0
2026-07-31 | Done | Update Dashboard with real Sofia observations | Live data instead of placeholders | Programming | Product Usefulness | 3 | 3 | 0 | pages/1_Dashboard.py
|  |  |  | Total Hours |  | 18 | 18 | 0
Week 14
week plan: | Collect the second Sofia photo set and run the first (unsuccessful) H3 routing sample.
Known Risks | City-wide risk coverage may be too sparse for a usable H3 sample.
2026-08-03 | Done | Plan second photo set | Sveta Troitsa, GPS needed | Planning | Project Management - Process | 1 | 1 | 0 | thesis 3.6
2026-08-03 | Done | Collect geotagged photos (session 1) | Standard camera app | Research | Research Methodology | 3 | 3 | 0 | data/manual/
2026-08-04 | Done | Run initial 40-route H3 sample (city-wide) | Random origin-destination pairs | Testing | Research Methodology | 3 | 3 | 0 | outputs/geo/route_comparison.json
2026-08-04 | Done | Discover only 4 risky edges citywide | No usable test result | Research | Project Management - Risk | 1.5 | 1.5 | 0 | thesis 4.1.3 | delayed test
2026-08-05 | Done | Collect geotagged photos (session 2) | Sveta Troitsa | Research | Research Methodology | 3 | 3 | 0 | data/manual/
2026-08-05 | Done | Collect geotagged photos (session 3) | Sveta Troitsa | Research | Research Methodology | 2 | 2 | 0 | data/manual/
2026-08-06 | Done | Process new photos through the pipeline | Detection + risk scoring | Programming | Research Methodology | 2 | 2 | 0 | outputs/geo/segment_risk.csv
2026-08-06 | Done | Derive neighbourhood evaluation boundary | From GPS extent of the photos | Research | Research Methodology | 2 | 2 | 0
|  |  |  | Total Hours |  | 17.5 | 17.5 | 0
Week 15
week plan: | Complete the remaining hypothesis tests: H3 (re-run), H4 and H2.
Known Risks | Manual segment rating is subjective; keep it blind to generated risk.
2026-08-10 | Done | Run second 40-route H3 sample | Restricted to neighbourhood nodes | Testing | Research Methodology | 2 | 2 | 0 | outputs/geo/route_comparison.json
2026-08-10 | Done | Run Wilcoxon on hazard exposure, check distance constraint | H3 statistical test | Research | Research Methodology | 2 | 2 | 0 | outputs/reports/
2026-08-11 | Done | Rate 16 road segments 1-5 | Both sessions, blind to generated risk | Research | Research Methodology | 4 | 4 | 0 | outputs/reports/h4_evaluation_results.csv
2026-08-11 | Done | Run Spearman correlations (total risk/density vs ratings) | H4 test | Research | Research Methodology | 1.5 | 1.5 | 0
2026-08-12 | Done | Select and label 42-image H2 sample | Independent, pre-model | Research | Research Methodology | 2.5 | 2.5 | 0 | outputs/reports/h2_evaluation_results.csv
2026-08-12 | Done | Run pipeline on H2 sample, compute accuracy/kappa/F1 | H2 statistics | Testing | Research Methodology | 2 | 2 | 0 | outputs/reports/h2_confusion_matrix.png
2026-08-13 | Done | Inspect detector output on H2 misses | Trace causes of under-scoring | Debugging | Research Methodology | 2 | 2 | 0 | thesis 4.1.4
2026-08-13 | Done | Supervisor check-in | Review H2/H3/H4 results before the qualitative study | Planning | Learning - Feedback | 0.5 | 0.5 | 0
2026-08-13 | Done | Draft H2/H3/H4 results notes | For later write-up | Evidencing | Professionalism - Communication | 2 | 2 | 0 | thesis 4.1
|  |  |  | Total Hours |  | 18.5 | 18.5 | 0
Week 16
week plan: | Run the first round of the usability study (5 participants) and fix the clearest issues found.
Known Risks | A 5-person pilot may be too small to settle every theme; keep it explicitly a pilot.
2026-08-24 | Done | Design usability survey and walkthrough script | 5 Likert + 4 open-ended questions | Design | Research Methodology | 2 | 2 | 0
2026-08-24 | Done | Recruit first 5 participants | No prior app experience | Meeting | Professionalism - Collaboration | 3 | 3 | 0 |  | Hard to find participants since the prototype is on local machine
2026-08-25 | Done | Run usability walkthroughs - P01-P03 | Guided session | Meeting | Product Usefulness | 3 | 3 | 0
2026-08-25 | Done | Run usability walkthroughs - P04-P05 | Guided session | Meeting | Product Usefulness | 2 | 2 | 0
2026-08-27 | Done | Compile closed-question stats and code themes (pilot, n=5) | First pass | Research | Research Methodology | 2.5 | 2.5 | 0 | outputs/reports/
2026-08-27 | Done | Identify interface issues raised by the pilot group | Alpha slider, pin selection unclear | Research | Project Management - Risk | 1.5 | 1.5 | 0 |  | issues found
2026-08-27 | Done | Supervisor check-in | Review pilot usability issues before round 2 | Planning | Learning - Feedback | 0.5 | 0.5 | 0 |  | I demoed the app to the supervisor and got feedback that everything works fine by now, but have to ellaborate everything in the thesis.
2026-08-28 | Done | Fix the clearest issues before the next round | Alpha-slider help text, map hint | Programming | Product Quality | 2 | 2 | 0 | pages/4_Safer_Route_Planner.py
2026-08-28 | Done | Final risk-config review | Last check before freezing | Research | Product Quality | 2 | 2 | 0 | config/risk_weights.yaml
|  |  |  | Total Hours |  | 18.5 | 18.5 | 0
Week 17
week plan: | Run the second round of the usability study (5 more, 10 total) and finalise/freeze the pipeline.
Known Risks | Re-coding themes with more participants may change earlier conclusions.
2026-08-31 | Done | Recruit 5 more participants | To reach 10 total | Meeting | Professionalism - Collaboration | 3 | 3 | 0 |  | Hard to find participants since the prototype is on local machine
2026-08-31 | Done | Run usability walkthroughs - P06-P08 | Guided session | Meeting | Product Usefulness | 3 | 3 | 0
2026-09-01 | Done | Run usability walkthroughs - P09-P10 | Guided session | Meeting | Product Usefulness | 2 | 2 | 0
2026-09-01 | Done | Recompute closed-question stats for n=10, regenerate chart | Full sample | Research | Research Methodology | 1.5 | 1.5 | 0 | outputs/reports/qualitative_survey_means_n10.png
2026-09-02 | Done | Code open-ended responses into 7 themes (full n=10) | Final thematic coding | Research | Research Methodology | 3 | 3 | 0 | thesis/qualitative_thematic_analysis.md
2026-09-02 | Done | Full pipeline smoke test end to end | RDD2022 image through to routing | Testing | Product Quality | 2.5 | 2.5 | 0
2026-09-03 | Done | Freeze model weights, risk config, app config | Final values locked | Programming | Product Quality | 2 | 2 | 0 | models/, config/
2026-09-03 | Done | Capture final application screenshots | Dashboard/Upload/Map/Route pages | Programming | Product Quality | 2 | 2 | 0 | screenshots/
|  |  |  | Total Hours |  | 19 | 19 | 0
Week 18
week plan: | Write Introduction, Related Work and Methodology, including the qualitative evaluation method.
Known Risks | Large writing volume; prioritise sections with stable, frozen numbers first.
2026-09-07 | Done | Write Introduction - context/problem/RQs | Section 1.1-1.2 | Evidencing | Professionalism - Communication | 3 | 3 | 0 | thesis section 1
2026-09-07 | Done | Write Introduction - approach overview, pipeline figure | Section 1.3 | Design | Professionalism - Communication | 2 | 2 | 0 | thesis section 1.3
2026-09-08 | Done | Write Related Work | Detection/architectures/risk/routing/gap | Evidencing | Professionalism - Communication | 3 | 3 | 0 | thesis section 2
2026-09-08 | Done | Write Methodology - dataset/models/risk scoring | Sections 3.1-3.3 | Evidencing | Professionalism - Communication | 3 | 3 | 0 | thesis section 3
2026-09-09 | Done | Write Methodology - routing/prototype sections | Sections 3.4-3.5 | Evidencing | Professionalism - Communication | 2.5 | 2.5 | 0 | thesis section 3
2026-09-09 | Done | Write Methodology - qualitative usability evaluation method | Survey design, walkthrough protocol, analysis plan | Evidencing | Research Methodology | 2 | 2 | 0 | thesis section 3.8
2026-09-09 | Done | Supervisor check-in | Feedback on Introduction/Related Work/Methodology draft | Planning | Learning - Feedback | 0.5 | 0.5 | 0 |  | We discussed the whole structure of the thesi and section ordering and formatting
2026-09-10 | Done | Build/insert remaining figures | Dataset examples, workflow diagram, worked example | Design | Professionalism - Communication | 2 | 2 | 0 | thesis/figures/
2026-09-10 | Done | Internal consistency pass on numbers written so far | Cross-check vs outputs/reports/ | Testing | Product Quality | 1.5 | 1.5 | 0
|  |  |  | Total Hours |  | 19.5 | 19.5 | 0
Week 19
week plan: | Write Results, Discussion, Ethics and Conclusion; final touches and proofread.
Known Risks | Compile/reference errors can surface late; leave time to fix them.
2026-09-14 | Done | Write Results - H1/H2 | Section 4.1 | Evidencing | Professionalism - Communication | 2.5 | 2.5 | 0 | thesis section 4.1
2026-09-14 | Done | Write Results - H3/H4, qualitative (n=10) | Section 4 | Evidencing | Professionalism - Communication | 2.5 | 2.5 | 0 | thesis section 4
2026-09-15 | Done | Write Discussion - H1, domain gap, H2 shortfall | Sections 5.1-5.3 | Evidencing | Professionalism - Communication | 2.5 | 2.5 | 0 | thesis section 5
2026-09-15 | Done | Write Discussion - H3/H4, limitations, implications, future work | Sections 5.4-5.7 | Evidencing | Professionalism - Communication | 3 | 3 | 0 | thesis section 5
2026-09-16 | Done | Write Ethics section | Section 6 | Evidencing | Professionalism - Ethics/Legal | 2 | 2 | 0 | thesis section 6
2026-09-16 | Done | Write Conclusion | Section 7 | Evidencing | Professionalism - Communication | 1.5 | 1.5 | 0 | thesis section 7
2026-09-17 | Done | Supervisor check-in | Feedback on the full thesis draft | Planning | Learning - Feedback | 0.5 | 0.5 | 0 |  | will have to add few more visuals and formula explanations
2026-09-17 | Done | Final abstract and title-page pass | Match final numbers | Evidencing | Professionalism - Communication | 1.5 | 1.5 | 0 | thesis abstract
2026-09-17 | Done | Full proofread and reference check | Whole document | Testing | Product Quality | 3 | 3 | 0
|  |  |  | Total Hours |  | 19 | 19 | 0
Week 20
week plan: | Final week: evidencing only.
Known Risks | Evidence links must point to the final, frozen versions of files.
2026-09-21 | Done | Finalise Work Log | All 20 weeks checked for accuracy | Evidencing | Project Management - Process | 2.5 | 2.5 | 0 | thesis/evidencing/
2026-09-21 | Done | Write Learning Log entries - Weeks 1-7 | Weekly reflections and feedback | Evidencing | Learning - Feedback | 2 | 2 | 0 | thesis/evidencing/
2026-09-22 | Done | Write Learning Log entries - Weeks 8-14 | Weekly reflections and feedback | Evidencing | Learning - Feedback | 2 | 2 | 0 | thesis/evidencing/
2026-09-22 | Done | Write Learning Log entries - Weeks 15-20 | Weekly reflections and feedback | Evidencing | Learning - Feedback | 2 | 2 | 0 | thesis/evidencing/
2026-09-23 | Done | Collect and organise evidence links | Code, thesis sections, outputs | Evidencing | Product Quality | 2.5 | 2.5 | 0
2026-09-23 | Done | Fill Assessment Rubric - ILO 1 (Research) | Relevance/Methodology/Application | Evidencing | Research Application | 2 | 2 | 0 | thesis/evidencing/
2026-09-24 | Done | Fill Assessment Rubric - ILO 2 (Product) | Usefulness/Quality | Evidencing | Product Quality | 2 | 2 | 0
2026-09-24 | Done | Fill Assessment Rubric - ILO 3 (Management) | Process/Risk/Problem-solving/Ethics | Evidencing | Project Management - Process | 2 | 2 | 0
2026-09-25 | Done | Fill Assessment Rubric - ILO 4 and 5 | Professionalism/Learning | Evidencing | Learning - Implementation | 2 | 2 | 0
2026-09-25 | Done | Final check-in | Confirm everything is ready before submission | Planning | Learning - Feedback | 0.5 | 0.5 | 0 |  | Got feedback to make minor changes to 2 small things in the thesis, but eveyrthing else looks fine by now
2026-09-25 | Done | Final review of all evidencing documents | Cross-check against portfolio | Testing | Product Quality | 2 | 2 | 0
|  |  |  | Total Hours |  | 21.5 | 21.5 | 0
|  |  |  | Total hours this block |  | 380.5 | 382.5 | 2

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
Research Relevance | W1: 0 | 0
Research Methodology | [8 empty] | 0
Research Application | [8 empty] | 0
Product Usefulness | [8 empty] | 0
Product Quality | [8 empty] | 0
Project Management - Process | [8 empty] | 0
Project Management - Risk | [8 empty] | 0
Professionalism - Collaboration | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | Research Relevance
Unplanned | Meeting | Research Methodology
Blocked | Programming | Research Application
In-Progress | Research | Product Usefulness
Done | Testing | Product Quality
Delayed | Workshop | Project Management - Process
Cancelled | Planning | Project Management - Risk
| Evidencing | Professionalism - Collaboration
| Debugging | Professionalism - Ethics/Legal
| Lecture | Professionalism - Communication
| Study | Learning - Feedback
| Unplanned | Learning - Implementation
Distraction
Break